## Sheet1
PROJECT TK DAILY PROGRESS |  |  | Project Detials
Date | Task | Status | Project Detials | PROJECT TK (Proper Name is Not Chosen)
2024-09-21 | Project Idea | Submitted | Project Idea | File Sharing And Storage
2024-09-23 | Database Schema | Done | Project Guide | Sohan Singh Sir
2024-09-23 | Data Flow Diagram | Done | Github Repositry | https://github.com/TanishkKumar0409/RegularPractice
2024-09-27 | Wireframe | Incomplete | Folder Name in Repositry | PROJECT TK
2024-09-30 | Wireframe | Done | Repositry Type | Private
2024-12-01 | Designing | Start | Tech | MERN Stack
2024-12-04 | Banner | Done | Project Deadline | 2024-01-15
2024-12-04 | Navigation | Done
2024-12-04 | Test Send Files | Done
2024-12-07 | Recent Files Section | Done
2024-12-10 | Shared Files History Table | Done
2024-12-10 | Footer | Working
2024-12-10 | Work on (Focus, Target Audience, Earning, Problem Solve) | Working